## Sheet1
Project Cost Estimation
Prepared by: Himabindu Poshala | Date: | 2018-05-24
WBS Items | # Units/Hr | Cost/Unit/Hr | Total | WBS Level 1 Totals
1. Project Management |  |  |  | 228000
1.1 Project manager | 700 | 110 | 77000
1.2 Project team members | 1400 | 90 | 126000
1.3 UI Designer | 500 | 50 | 25000
2. Hardware |  |  |  | 40000
2.1 Handheld devices | 60 | 500 | 30000
2.2 Servers | 5 | 5000 | 10000
3. Software |  |  |  | 308400
3.1 Licensed software | 60 | 140 | 8400
3.2 Software development |  |  | 300000
4. Testing |  |  | 34445 | 34445
5. Training and Support |  |  |  | 94900
5.1 Trainee cost | 70 | 470 | 32900
5.2 Travel cost | 10 | 700 | 7000
5.3 Project team members | 1000 | 55 | 55000
6. Reserves (20% of total estimate) |  |  | 130500 | 130500
Total Project Cost Estimate |  |  |  | 836245